## Sheet1
USER ID | USER STORY | PRIORITY | RISK | STORY POINTS
1 | As a new customer, I want to register an account so that I can use online banking. | must do | medium | 5
2 | As a customer, I want to log in using identity verification to secure my financial data. | must do | high | 8
3 | As a customer, I want to see a consolidated dashboard of all my active accounts and balances. | must do | low | 3
4 | As a customer, I want to update my email and phone number to keep my profile current. | should do | low | 2
5 | As an authenticated customer, I want to initiate a deposit to instantly increase my balance. | must do | high | 5
6 | As an authenticated customer, I want to withdraw cash to securely access my physical funds. | must do | high | 5
7 | As a customer, I want to transfer funds to another internal account to pay someone quickly. | must do | high | 5
8 | As a customer, I want to view my transaction history to track my spending over time. | should do | low | 3
9 | As a customer, I want to download monthly e-statements as a PDF for legal and tax records. | could do | medium | 5
10 | As a customer, I want to reset my forgotten password via email verification to regain account access. | must do | medium | 5
11 | As a customer, I want to close an empty account online if I no longer intend to use it. | could do | medium | 3
12 | As a bank employee, I want to review pending customer registrations to verify their identities. | must do | medium | 5
13 | As a bank employee, I want to search for customer accounts by name or account number to assist them. | must do | low | 3
14 | As a bank employee, I want to flag suspicious high-value transactions for fraud investigation. | must do | high | 8
15 | As a bank employee, I want to manually override and adjust incorrect transaction entries to fix errors. | should do | high | 5
16 | As a system admin, I want to assign specific access permissions to bank employees to secure operations. | must do | high | 5
17 | As a system admin, I want to view a system audit log of all account modifications to track changes. | should do | medium | 5
18 | As a system admin, I want to temporarily lock compromised customer accounts to stop active breaches. | must do | high | 3
19 | As a system admin, I want to configure global withdrawal limits across the system to mitigate risk. | should do | medium | 3
20 | As a system admin, I want to extract end-of-day operational reports to monitor daily health. | could do | low | 5

## Sheet2
USER ID | SPRINT | USER STORY | STORY POINTS | PRIORITY | RISK | USER ID on which dependant
1 | 1 | As a new customer, I want to register an account so that I can use online banking. | 5 | must do | medium
2 | 1 | As a customer, I want to log in using identity verification to secure my financial data. | 8 | must do | high | 1
12 | 1 | As a bank employee, I want to review pending customer registrations to verify their identities. | 5 | must do | medium | 1, 16
16 | 1 | As a system admin, I want to assign specific access permissions to bank employees to secure operations. | 5 | must do | high
SPRINT 1 TOTAL STORY POINTS 23
3 | 2 | As a customer, I want to see a consolidated dashboard of all my active accounts and balances. | 3 | must do | low | 2
4 | 2 | As a customer, I want to update my email and phone number to keep my profile current. | 2 | should do | low | 2
5 | 2 | As an authenticated customer, I want to initiate a deposit to instantly increase my balance. | 5 | must do | high | 2
6 | 2 | As an authenticated customer, I want to withdraw cash to securely access my physical funds. | 5 | must do | high | 2
7 | 2 | As a customer, I want to transfer funds to another internal account to pay someone quickly. | 5 | must do | high | 2
18 | 2 | As a system admin, I want to temporarily lock compromised customer accounts to stop active breaches. | 3 | must do | high | 2, 16
SPRINT 2 TOTAL STORY POINTS 23
8 | 3 | As a customer, I want to view my transaction history to track my spending over time. | 3 | should do | low | 5, 6, 7
10 | 3 | As a customer, I want to reset my forgotten password via email verification to regain account access. | 5 | must do | medium | 1
13 | 3 | As a bank employee, I want to search for customer accounts by name or account number to assist them. | 3 | must do | low | 12, 16
14 | 3 | As a bank employee, I want to flag suspicious high-value transactions for fraud investigation. | 8 | must do | high | 5, 6, 7, 16
19 | 3 | As a system admin, I want to configure global withdrawal limits across the system to mitigate risk. | 3 | should do | medium | 6, 16
SPRINT 3 TOTAL STORY POINTS 22
9 | 4 | As a customer, I want to download monthly e-statements as a PDF for legal and tax records. | 5 | could do | medium | 8
11 | 4 | As a customer, I want to close an empty account online if I no longer intend to use it. | 3 | could do | medium | 2
15 | 4 | As a bank employee, I want to manually override and adjust incorrect transaction entries to fix errors. | 5 | should do | high | 8, 16
17 | 4 | As a system admin, I want to view a system audit log of all account modifications to track changes. | 5 | should do | medium | 4, 5, 6, 7, 15, 16
20 | 4 | As a system admin, I want to extract end-of-day operational reports to monitor daily health. | 5 | could do | low | 5, 6, 7, 14, 17
SPRINT 4 TOTAL STORY POINTS 23

## Sheet3
DEPENDENCY TABLE
Serial No | USER ID | DEPENDANT ON
1 | 2 | 1
2 | 3 | 2
3 | 4 | 2
4 | 5 | 2
5 | 6 | 2
6 | 7 | 2
7 | 8 | 5, 6, 7
8 | 9 | 8
9 | 10 | 1
10 | 11 | 2
11 | 12 | 1, 16
12 | 13 | 12, 16
13 | 14 | 5, 6, 7, 16
14 | 15 | 8, 16
15 | 17 | 4, 5, 6, 7, 15, 16
16 | 18 | 2, 16
17 | 19 | 6, 16
18 | 20 | 5, 6, 7, 14, 17